PRODUCT DELIVERY GUIDE

Little Gains

Full product roadmap and execution checklist

A mobile-first path from the validated core journey to helpful reminders, optional calendar awareness, beta, and launch - one approved phase at a time.

| Product | Little Gains |
| --- | --- |
| Purpose | Guide phased delivery, review, and approval |
| Last updated | 30 August 2026 |
| Current state | Phase 4 implementation approved; reminder trial and usability validation remain open |

NEXT RECOMMENDED PHASE Defer optional calendar awareness and proceed to Phase 6 quality hardening and private-beta preparation while completing the reminder trial and five-user usability validation.

# Guiding principles

Small wins over dramatic plans: every action must have a low-energy version.

Helpful, not nagging: prompts respect quiet hours, daily caps, and 'bad time' feedback.

Calendar optional: the app remains fully useful without company permissions or meeting access.

Private by default: sensitive routine and health-adjacent data stays local unless the user explicitly opts in.

Progress without shame: use cumulative gains and neutral reflection, never punitive streaks.

How to use this guide

Review the current phase checklist, confirm its exit gate, and approve the next phase before implementation begins. Calendar, analytics, accounts, and health integrations each require a separate decision.

# 1. Current baseline

STATUS The core journey, reminders, routine editing, reflection, and personalization are implemented and verified on a connected Samsung device. The encrypted database and history survive restart and upgrade.

## Already delivered

Expo SDK 57 mobile foundation with calm light and dark nature-led design tokens.

Five-step onboarding for name, priorities, work routine, mobility preference, and starter plan.

Adaptive Today experience with low, steady, strong, and very-busy energy modes.

Five curated habits, a maximum of three active habits, and next-day plan changes.

Guided habit sessions, cumulative wins, movement minutes, sitting breaks, and a neutral seven-day chart.

Encrypted SQLCipher persistence with a device-bound key stored in SecureStore.

Automated checks for the implemented journey plus native-device persistence validation.

## Known boundaries

The one-week reminder usefulness trial remains open.

Five-user routine-editing and reflection validation remains open.

Calendar access is not connected; meeting-aware prompts remain optional future work.

There is no account, cloud sync, wearable integration, production analytics, or store release pipeline.

## Roadmap at a glance

| Milestone | Status | Outcome | Exit gate |
| --- | --- | --- | --- |
| M0 | Complete | Technical foundation | Secure native shell verified |
| M1 | Complete | Core habit journey | Onboarding, Today, Habits, Journey, persistence verified |
| M2 | Implemented | Reminder-ready MVP | Technical checks pass; one-week trial open |
| M3 | Implemented | Personalized beta | Implementation approved; five-user trial open |
| M4 | Deferred | Calendar-aware support | Consent, fallback, and privacy gate passed |
| M5 | In progress | Hardened beta | Accessibility, reliability, privacy, and pilot exit criteria pass |
| M6 | Pending | Public launch | Store, support, policy, and release checks pass |
| M7 | Later | Post-launch expansion | Chosen only from observed user needs |

# 2. Phase 3 - Timely support and reminders

Status: IMPLEMENTED AND APPROVED - one-week trial open

Objective: Help the user remember small actions at suitable moments without requiring calendar access.

PRODUCT BEHAVIOR The user provides workdays, work hours, and a lunch window. The app proposes prompt windows, asks for notification permission only after explaining the benefit, and learns from simple responses such as Done, Later, Bad time, and Not today.

## How it works without meetings or meal data

Onboarding supplies the broad work and lunch windows; the app does not guess exact meal times.

The app schedules a small number of local prompts inside those windows and avoids quiet hours.

A prompt offers one-tap outcomes: Done, Later, Bad time, or Not today.

Repeated 'bad time' feedback shifts future windows; it does not reduce or shame the user's progress.

Meeting resets remain available manually until an optional calendar integration is approved.

## Implementation checklist

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| DONE | Reminder preference screen | User can enable or disable each prompt family and see an example before granting permission. |
| DONE | Permission education | System permission appears only after a plain-language explanation; denial leaves the app fully usable. |
| DONE | Local notification scheduler | Prompts respect selected workdays, work hours, lunch window, timezone, and quiet hours. |
| DONE | Prompt actions | Done records a win; Later reschedules; Bad time records preference; Not today closes the prompt neutrally. |
| DONE | Daily cap and cooldown | No duplicate or back-to-back prompts; user-selectable low, normal, or high support level. |
| DONE | Schedule recovery | Pending prompts recover after app restart, device restart, timezone change, and daylight-saving changes. |
| DONE | In-app reminder center | User can view the next planned prompt, pause today, or pause all reminders. |
| DONE | Accessibility and tone QA | Actions are screen-reader labeled, large-text safe, and use supportive, non-medical language. |
| DONE | Automated and device tests | Scheduling logic, action handling, denial flow, and native background behavior pass on target devices. |

## Exit gate

APPROVAL CHECK Implementation is approved. Close after a one-week trial confirms reminders are easy to disable, stay inside allowed windows, recover reliably, and feel helpful.

# 3. Phase 4 - Personalization and weekly reflection

Status: IMPLEMENTED AND APPROVED - five-user validation open

Objective: Let the app evolve with real life while keeping plans small and manageable.

## Core decisions

Edits apply predictably: routine and habit changes show exactly when they take effect.

Adaptation uses explicit feedback and recent completion patterns, not opaque scoring.

The weekly reflection asks what helped and what got in the way; it never penalizes missed days.

A low-energy plan is always available and counts as a complete small win.

## Implementation checklist

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| DONE | Editable profile and routine | Name, priorities, workdays, hours, lunch window, mobility, and reminder level can be changed. |
| DONE | Plan change preview | Before saving, the user sees which prompts and habits change today versus tomorrow. |
| DONE | Weekly reflection | A two-minute flow captures helpfulness, difficulty, energy, and one adjustment. |
| DONE | Transparent adaptation | Each suggested change includes a reason and can be accepted, modified, or dismissed. |
| DONE | Flexible habit library | Curated habits support minimum and standard versions, mobility alternatives, and safety notes. |
| DONE | Reset and recovery | The user can restart onboarding choices or return to a simple starter plan without losing history. |
| DONE | Journey insight cards | Insights summarize cumulative behavior without streak loss, ranking, or guilt language. |
| VALIDATE | Usability validation | Five representative work-from-home users complete edit and reflection tasks without guidance. |

## Exit gate

APPROVAL CHECK Implementation is approved. Close after five users edit a routine in under two minutes, understand suggested changes, and retain control of timing and intensity.

# 4. Phase 5 - Optional calendar-aware support

Status: DEFERRED - manual scheduling remains the complete baseline

Objective: Avoid unsuitable prompt moments using the minimum calendar information necessary.

RECOMMENDATION Do not start here. First learn whether time-window reminders are genuinely useful. Then choose between device-calendar access and Microsoft Graph based on user evidence and company permission constraints.

## Integration options

| Path | Strengths | Constraints | Best fit |
| --- | --- | --- | --- |
| A. Device calendar | Platform consent; can read busy windows from calendars already on the phone. | Platform-specific behavior; users may have several calendars; permissions remain sensitive. | Fastest route to local, read-only busy-time awareness. |
| B. Outlook / Microsoft Graph | Direct Microsoft account connection and clearer enterprise-calendar scope. | Company tenant policy may require administrator approval; OAuth and token handling add complexity. | Users whose work calendar is authoritative in Microsoft 365. |
| C. Manual only | No account or calendar permission; fully private and reliable fallback. | Cannot automatically avoid meetings; asks the user to adjust or snooze prompts. | Required baseline even if A or B is later added. |

## Privacy contract

Calendar connection is opt-in and can be revoked from the app at any time.

Use start time, end time, and busy/free status only; do not store titles, attendees, notes, or meeting links.

Compute safe prompt windows locally whenever the chosen platform permits it.

Show what data is accessed, why it is needed, and how long any token or derived window is retained.

Manual scheduling remains a complete path if consent is declined or company administration blocks access.

## Implementation checklist

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| TO DO | Discovery decision | User evidence selects device calendar, Microsoft Graph, both in sequence, or no integration. |
| TO DO | Permission feasibility | Test account and company-tenant scenarios document when administrator consent is required. |
| TO DO | Consent and revoke flow | The user can connect, inspect scope, disconnect, and return to manual mode without data loss. |
| TO DO | Busy-window model | Only free/busy timing is retained; sensitive event content is excluded by design and test. |
| TO DO | Conflict-aware scheduling | Prompts do not fire during busy windows and recover sensibly after meetings move or cancel. |
| TO DO | Offline and error handling | Expired tokens, no network, revoked permissions, and tenant blocks degrade to manual scheduling. |
| TO DO | Security review | Token storage, redirect handling, logs, telemetry, and deletion behavior pass review. |

## Exit gate

APPROVAL CHECK Ship calendar awareness only if it measurably reduces poorly timed prompts, exposes no event content, and preserves a first-class manual experience.

# 5. Phase 6 - Quality hardening and private beta

Status: IN REVIEW - Android release verified; pilot gates remain

Objective: Make the app dependable, accessible, private, and understandable for a small pilot group.

## Hardening checklist

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| IN REVIEW | Accessibility | Large text through 150%, reduced motion, high-contrast text, 48-point targets, and practical one-handed reachability pass on the Samsung release build. TalkBack labels and the guided flow pass a device smoke check; human spoken-output and gesture validation remains. |
| IN REVIEW | Reliability | Migration and integrity tests pass; encrypted data survived upgrade and restart. Scheduled reminders clear on deletion; forced corruption recovery remains. |
| IN REVIEW | Cross-device coverage | The current Samsung passed upgrade, fresh onboarding, restart, export, and deletion. API 24 and supported iOS coverage remain. |
| DONE | Privacy review | Local data and permissions match the promise. JSON export excludes keys and OS identifiers; disposable-profile deletion cleared data and scheduled alarms immediately. |
| DONE | Safety review | Mobility alternatives, stop conditions, and a non-medical disclaimer pass review. |
| IN REVIEW | Performance | Cold starts measured 479-555 ms versus a three-second budget. Other interaction timing remains a pilot check. |
| READY | Private beta distribution | EAS internal preview and its distribution checklist are ready; external builds await credential approval. |
| DONE | Pilot support | The beta runbook covers tasks, intake, device coverage, severity, rollback, and exit criteria. |

## Suggested beta design

PILOT DESIGN Recruit 10-30 work-from-home adults with varied schedules and mobility needs for two weeks. Compare manual timing with refined reminder settings; use only opt-in minimal analytics and short interviews. Review prompt helpfulness, bad-time rate, one-small-win days, seven-day return, and reasons reminders are disabled. Do not collect calendar content or medical data.

## Exit gate

APPROVAL CHECK Move to launch preparation only when no open critical defects remain, core accessibility checks pass, privacy promises match implementation, and pilot feedback supports continued use.

# 6. Phase 7 - Launch readiness

Status: PENDING - starts after beta exit approval

Objective: Prepare a trustworthy, supportable public release without expanding the core scope.

## Launch checklist

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| TO DO | Release scope lock | Launch includes the validated core and reminders; calendar remains optional if its gate is not met. |
| TO DO | Store identity | Final icon, screenshots, description, age rating, categories, and calm nature-led presentation are approved. |
| TO DO | Policies | Privacy policy, terms, permissions explanation, non-medical disclaimer, and support contact are published. |
| TO DO | Signing and builds | Production certificates, Android App Bundle, iOS archive, versioning, and reproducible build steps are verified. |
| TO DO | Release testing | Fresh install, upgrade, denial paths, offline use, notification timing, and data persistence pass release candidates. |
| TO DO | Observability | Privacy-minimal crash reporting and operational alerts are configured with no habit or calendar content. |
| TO DO | Support operations | FAQ, contact route, response targets, incident process, and rollback criteria are ready. |
| TO DO | Store submission | Google Play and Apple review requirements are met and reviewer notes explain optional permissions. |

## Launch definition

LAUNCHABLE A user can install, understand the promise, create a small plan, receive respectful reminders, complete a habit, review cumulative gains, change or pause support, and delete or retain their local data with confidence.

# 7. Phase 8 - Post-launch learning and expansion

Status: LATER - each item needs its own approval and evidence

Objective: Extend Little Gains only where real user needs justify additional complexity or data access.

## Candidate backlog

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| TO DO | Health platform integration | Apple Health / Health Connect adds clear value, asks narrow permissions, and never becomes mandatory. |
| TO DO | Wearable cues | Watch prompts are quieter and more useful than phone prompts in a measured pilot. |
| TO DO | Optional account and sync | Cross-device value outweighs new security, identity, backup, and deletion responsibilities. |
| TO DO | Expanded habit content | New movement, hydration, focus, sleep-wind-down, and recovery ideas have safe alternatives and evidence review. |
| TO DO | Deeper personalization | Rules remain explainable and can operate locally; AI is not added unless a specific benefit is proven. |
| TO DO | Social support | Any accountability feature is opt-in, private, noncompetitive, and avoids public streaks or rankings. |
| TO DO | Localization | Language, cultural context, units, schedules, and accessibility are adapted rather than merely translated. |

## Explicitly outside the near-term scope

Diagnosis, treatment, medical monitoring, or claims that the app prevents disease.

Calorie counting, weight-loss pressure, body comparison, or public leaderboards.

Mandatory accounts, cloud sync, calendar access, or employer visibility.

High-frequency engagement loops, punitive streaks, or notifications designed only to increase screen time.

# 8. Execution guide

SCHEDULING NOTE The 90-day view is illustrative, not a commitment. A phase starts only after the previous exit gate is reviewed and explicitly approved.

## Illustrative 90-day sequence

| Timing | Focus | Primary work | Decision gate |
| --- | --- | --- | --- |
| Weeks 1-2 | Phase 3 | Reminder preferences, permission flow, local scheduler, actions | Approve reminder behavior |
| Weeks 3-4 | Phase 4 | Routine editing, weekly reflection, transparent adaptation | Approve personalized beta |
| Weeks 5-7 | Phase 5 or hardening | Calendar discovery/prototype only if approved; otherwise accelerate quality work | Choose calendar path or defer |
| Weeks 8-10 | Phase 6 | Accessibility, reliability, privacy review, private beta | Approve launch preparation |
| Weeks 11-12 | Phase 7 | Store assets, policies, release candidates, support readiness | Approve public submission |

## Definition of done for every phase

| Check | Action | Acceptance evidence |
| --- | --- | --- |
| TO DO | Product intent | The user problem, scope, non-goals, and acceptance criteria are written and approved. |
| TO DO | UX states | Happy path, empty, loading, denied, paused, offline, error, and recovery states are designed. |
| TO DO | Privacy and permissions | New data, permissions, retention, deletion, logs, and fallback behavior are reviewed. |
| TO DO | Implementation | Code follows project conventions, migrations are safe, and long functions contain explanatory comments. |
| TO DO | Automated verification | Type checks, lint, unit/integration tests, and relevant build checks pass. |
| TO DO | Device verification | The changed journey is tested on a real target device and, where relevant, after restart or upgrade. |
| TO DO | Accessibility | Labels, focus, text scaling, contrast, motion, touch targets, and alternative actions pass. |
| TO DO | Documentation | Roadmap status, decisions, known limitations, and user-facing guidance are updated. |
| TO DO | Approval | A concise phase report is reviewed and explicit permission to commit or proceed is received. |

## Approval checkpoint template

Phase reviewed: ____________________________

Evidence reviewed: ____________________________

Open risks or deferrals: ____________________________

Decision: Approve / Revise / Defer (circle one)

Approved by / date: ____________________________

# 9. Learning, success, and risk controls

## Success signals

Onboarding completion: users can create a starter plan without confusion or abandoning permissions screens.

One-small-win days: the share of active days with at least one completed action increases over time.

Prompt helpfulness: users mark prompts helpful more often than Bad time or Not today.

Control and trust: users can easily pause, change, or disable reminders without losing their plan.

Sustainable return: seven- and thirty-day return is interpreted with interviews, not used to justify nagging.

Accessibility and reliability: critical journeys pass agreed checks and crash-free sessions remain high.

MEASUREMENT RULE Prefer opt-in, minimal event data. Never log habit notes, calendar content, mobility limitations, or personally revealing free text merely to improve analytics.

## Risk register

| Risk | Control |
| --- | --- |
| Notification fatigue | Daily caps, quiet hours, support levels, pause controls, and bad-time learning. |
| Outlook access blocked | Manual mode remains complete; test tenant policy early; consider device calendar as a separate option. |
| Background scheduling differences | Platform-specific tests, recovery after reboot/timezone change, and visible next-prompt status. |
| Sensitive data exposure | Local-first design, narrow permissions, encrypted storage, minimal logs, and explicit deletion paths. |
| Medical or safety overreach | General wellbeing language, mobility alternatives, stop conditions, and no diagnosis or treatment claims. |
| Scope creep | Phase gates, launch boundary, candidate backlog, and explicit approval before accounts, calendar, analytics, or integrations. |
| Shame-based engagement | Cumulative gains, neutral reflection, low-energy wins, and no punitive streaks or public rankings. |

## Immediate next decision

APPROVED NEXT PHASE Defer Phase 5 calendar access. Proceed to Phase 6 quality hardening and private-beta preparation while completing the open Phase 3 reminder trial and Phase 4 five-user usability validation.

Document status: updated through Phase 6 review. Calendar deferred; reminder and usability trials remain open.